## Dashboard
DOKO — Project Management Workbook
ST4008CEM · Softwarica College of IT & E-commerce · Coventry University
KEY PROJECT METRICS
| Total Features | Completed | In Progress | Not Started | % Complete | Sprints
| 24 | 24 | 0 | 0 | 100% | 5
PRIORITY
■ HIGH |  | ■ MEDIUM |  | ■ LOW
STATUS
■ NOT STARTED |  | ■ IN PROGRESS |  | ■ DONE |  | ■ PLANNED
FEATURES BY MODULE |  |  |  |  | FEATURES BY PRIORITY
Module | Features | Story Pts |  |  | Priority | Count
Authentication | 4 | 13 |  |  | High | 9
User Management | 2 | 6 |  |  | Medium | 8
Dashboard | 2 | 7 |  |  | Low | 7
Order Management | 3 | 16
Order History | 2 | 10
Tracking & Logistics | 4 | 18
Operations | 2 | 10
Branch & Pricing | 2 | 13
Monitoring & Admin | 2 | 10
Notifications | 1 | 3
SPRINT SUMMARY
Sprint | Features | Story Points | Module Focus | Status
Sprint 1 | 5 | 15 | Authentication & Dashboard | Completed
Sprint 2 | 7 | 30 | Order Management, History & Pricing | Completed
Sprint 3 | 6 | 26 | Logistics, Operations & Admin | Completed
Sprint 4 | 4 | 20 | Tracking, Operations & Dashboard | Completed
Sprint 5 | 2 | 8 | Monitoring & Admin | Completed

## User Stories
DOKO — AGILE USER STORY
Feature ID | User Story ID | Feature Name | Module | As a <Type of user> I need to <perform some task> | So that I can <achieve something> | User Story (full) | Priority | Status | Sprint | Effort (pts) | Complexity
F1 | 1.1 | User Registration | Authentication | register with my name, email, phone, and password | I can create a DOKO account and access the platform. | As a new visitor, I want to register with my name, email, phone, and password so that I can create a DOKO account and access the platform. | High | Completed | Sprint 1 | 3 | Medium
F2 | 2.1 | User Login | Authentication | log in with my email and password | I can access my role-specific dashboard. | As a registered user, I want to log in with my email and password so that I can access my role-specific dashboard. | High | Completed | Sprint 1 | 3 | Medium
F3 | 3.1 | OTP-Based Password Reset | Authentication | request a password reset OTP to my email and use it to set a new password | I can securely regain access to my account if I forget my password. | As a registered user, I want to request a password reset OTP to my email and use it to set a new password so that I can securely regain access to my account if I forget my password. | High | Completed | Sprint 1 | 5 | Medium
F4 | 4.1 | Profile Edit | Account Management | edit my name, phone number, and address | I can keep my profile information up to date. | As a logged-in user, I want to edit my name, phone number, and address so that I can keep my profile information up to date. | High | Completed | Sprint 2 | 3 | Medium
F5 | 5.1 | Role-Based Dashboard Redirect | Dashboard | be automatically redirected to my role-specific dashboard after login | I can immediately see only the features relevant to my role. | As a logged-in user, I want to be automatically redirected to my role-specific dashboard after login so that I can immediately see only the features relevant to my role. | High | Completed | Sprint 1 | 2 | Medium
F6 | 6.1 | Order Form Submission | Order Management | fill out an order form with receiver details, parcel weight, and description | I can create a new delivery order in the system. | As a Sender, I want to fill out an order form with receiver details, parcel weight, and description so that I can create a new delivery order in the system. | High | Completed | Sprint 2 | 8 | Medium
F7 | 7.1 | Forgot password | Authentication | change the password if i forgot | I can login again | As a Sender, I want to change the password if i forgot so that I can login again | High | Completed | Sprint 1 | 2 | Medium
F8 | 8.1 | Sender Order History | Order Management | view a list of all my past and current orders with their statuses | I can stay informed about all my deliveries in one place. | As a Sender, I want to view a list of all my past and current orders with their statuses so that I can stay informed about all my deliveries in one place. | High | Completed | Sprint 2 | 5 | Medium
F9 | 9.1 | Public Parcel Tracking | Tracking | enter a Tracking ID on the website without logging in | I can quickly check the current status and last updated location of a parcel. | As a Sender or Receiver, I want to enter a Tracking ID on the website without logging in so that I can quickly check the current status and last updated location of a parcel. | Medium | Completed | Sprint 5 | 3 | Medium
F10 | 10.1 | Order Cancellation | Order Management | cancel an order that has not yet been picked up | I can avoid being charged for a delivery I no longer need. | As a Sender, I want to cancel an order that has not yet been picked up so that I can avoid being charged for a delivery I no longer need. | High | Completed | Sprint 2 | 3 | Medium
F11 | 11.1 | Assigned Orders View | Employee Tools | view a list of all orders assigned to me | I can know exactly what parcels I need to pick up or deliver. | As an Employee, I want to view a list of all orders assigned to me so that I can know exactly what parcels I need to pick up or deliver. | Medium | Completed | Sprint 4 | 5 | Medium
F12 | 12.1 | Transit Checkpoint Status Update | Tracking | update the parcel status at each transit checkpoint | I can keep the tracking log accurate as the parcel moves across branches. | As a Station Staff member, I want to update the parcel status at each transit checkpoint so that I can keep the tracking log accurate as the parcel moves across branches. | Low | Completed | Sprint 4 | 5 | Medium
F13 | 13.1 | Delivery Confirmation & Timestamp | Tracking | mark an order as Delivered once the Receiver has the parcel | I can record the delivery timestamp and close the order. | As a Last-Mile Employee, I want to mark an order as Delivered once the Receiver has the parcel so that I can record the delivery timestamp and close the order. | Medium | Completed | Sprint 4 | 5 | Medium
F14 | 14.1 | Employee Order History | Employee Tools | view all orders I have previously handled | I can keep track of my own delivery history and performance. | As an Employee, I want to view all orders I have previously handled so that I can keep track of my own delivery history and performance. | Low | Completed | Sprint 2 | 5 | Medium
F15 | 15.1 | Active Orders Dashboard | Dashboard | see a dashboard of all currently active orders across all employees | I can monitor the overall flow of parcels in real time. | As a Manager, I want to see a dashboard of all currently active orders across all employees so that I can monitor the overall flow of parcels in real time. | Medium | Completed | Sprint 4 | 5 | Medium
F16 | 16.1 | Employee Workload Monitor | Dashboard | see how many active orders each Employee currently has | I can quickly spot overloading and act before delays happen. | As a Manager, I want to see how many active orders each Employee currently has so that I can quickly spot overloading and act before delays happen. | Low | Completed | Sprint 5 | 5 | Medium
F17 | 17.1 | Order Filter by Status / Branch | Order Management | filter orders by status or branch location | I can focus on problem areas and resolve issues faster. | As a Manager, I want to filter orders by status or branch location so that I can focus on problem areas and resolve issues faster. | Low | Completed | Sprint 3 | 5 | Medium
F18 | 18.1 | User Account Management | Admin Tools | create, edit, or deactivate any user account and change their role | I can ensure the right people have the right level of access at all times. | As an Admin, I want to create, edit, or deactivate any user account and change their role so that I can ensure the right people have the right level of access at all times. | Medium | Completed | Sprint 3 | 3 | Medium
F19 | 19.1 | Manual Order Edit | Admin Tools | manually edit any field in the Orders table | I can fix data errors or make price adjustments without any system restrictions. | As an Admin, I want to manually edit any field in the Orders table so that I can fix data errors or make price adjustments without any system restrictions. | Low | Completed | Sprint 2 | 5 | Medium
F20 | 20.1 | Branch Location Management | Admin Tools | add, edit, or remove transit branch locations | I can keep the system's network map aligned with real-world operations. | As an Admin, I want to add, edit, or remove transit branch locations so that I can keep the system's network map aligned with real-world operations. | Medium | Completed | Sprint 3 | 5 | Medium
F21 | 21.1 | Pricing Rule Configuration | Admin Tools | set and update pricing rules such as price per kg or per km | I can ensure delivery charges are calculated correctly and automatically. | As a Admin, I want to set and update pricing rules such as price per kg or per km so that I can ensure delivery charges are calculated correctly and automatically. | Medium | Completed | Sprint 2 | 8 | Medium
F22 | 22.1 | Automated Email Notification | Notifications | receive an automatic email notification whenever my parcel's status changes | I can stay updated without having to manually check the tracking page. | As a Sender or Receiver, I want to receive an automatic email notification whenever my parcel's status changes so that I can stay updated without having to manually check the tracking page. | Low | Completed | Sprint 3 | 3 | Medium
F23 | 23.1 | Return-to-Sender Flow | Order Management | trigger a Return-to-Sender flow by swapping the sender and receiver IDs | I can handle undeliverable parcels cleanly without creating a new order. | As an Employee or Admin, I want to trigger a Return-to-Sender flow by swapping the sender and receiver IDs so that I can handle undeliverable parcels cleanly without creating a new order. | Low | Completed | Sprint 3 | 5 | Medium
F24 | 24.1 | Parcel Status History Timeline | Tracking | view the full status history timeline of a parcel | I can see every checkpoint it passed through from Pending all the way to Delivered. | As a logged-in user, I want to view the full status history timeline of a parcel so that I can see every checkpoint it passed through from Pending all the way to Delivered. | Medium | Completed | Sprint 3 | 2 | Medium

## Module Summary
DOKO — MODULE & SPRINT ANALYSIS
FEATURE COUNT BY MODULE
Module | Total Features | Completed | In Progress | Not Started | Story Points
Authentication | 4 | 4 | 0 | 0 | 13
User Management | 2 | 2 | 0 | 0 | 6
Dashboard | 2 | 2 | 0 | 0 | 7
Order Management | 3 | 3 | 0 | 0 | 16
Order History | 2 | 2 | 0 | 0 | 10
Tracking & Logistics | 4 | 4 | 0 | 0 | 18
Operations | 2 | 2 | 0 | 0 | 10
Branch & Pricing | 2 | 2 | 0 | 0 | 13
Monitoring & Admin | 2 | 2 | 0 | 0 | 10
Notifications | 1 | 1 | 0 | 0 | 3
FEATURE COUNT BY PRIORITY
HIGH | MEDIUM | Low
F1User Registration | F6User Account Management | F10Manual Order Edit
F2User Login | F8Active Orders Dashboard | F13Employee Order History
F3Forgot Password | F14Public Parcel Tracking | F16Transit Checkpoint Status Update
F4OTP-Based Password Reset | F15Parcel Status History Timeline | F18Return-to-Sender Flow
F5Profile Edit | F17Delivery Confirmation & Timestamp | F22Employee Workload Monitor
F7Role-Based Dashboard Redirect | F19Assigned Orders View | F23Order Filter by Status / Branch
F9Order Form Submission | F20Branch Location Management | F24Automated Email Notification
F11Order Cancellation | F21Pricing Rule Configuration
F12 Sender Order History
Total:9 | Total:8 | Total:7
STORY POINTS PER SPRINT
Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5
15 | 30 | 26 | 20 | 8

## Acceptance Criteria
DOKO — ACCEPTANCE CRITERIA DETAIL VIEW
Feature ID | User Story ID | Feature Name | Module | Criterion | Criterion Text | Status
F1 | 1.1 | User Registration | Authentication | AC1 | When valid registration details are submitted, then the account is created successfully. | Completed
F1 | 1.1 | User Registration | Authentication | AC2 | When invalid input is provided, then appropriate error messages are shown. | Completed
F1 | 1.1 | User Registration | Authentication | AC3 | When an email already exists, then registration is denied. | Completed
F1 | 1.1 | User Registration | Authentication | AC4 | When registration is successful, then a confirmation email is sent. | Completed
F2 | 2.1 | User Login | Authentication | AC1 | When valid email and password are entered, then the user is logged in successfully. | Completed
F2 | 2.1 | User Login | Authentication | AC2 | When invalid credentials are entered, then an error message is displayed. | Completed
F2 | 2.1 | User Login | Authentication | AC3 | When the account is deactivated, then login is denied. | Completed
F2 | 2.1 | User Login | Authentication | AC4 | When login is successful, then the user is redirected to their role-specific dashboard. | Completed
F3 | 3.1 | OTP-Based Password Reset | Authentication | AC1 | When a registered email is submitted, then an OTP is sent to the email address. | Completed
F3 | 3.1 | OTP-Based Password Reset | Authentication | AC2 | When a valid OTP is entered, then the user can set a new password. | Completed
F3 | 3.1 | OTP-Based Password Reset | Authentication | AC3 | When an invalid or expired OTP is entered, then an error message is displayed. | Completed
F3 | 3.1 | OTP-Based Password Reset | Authentication | AC4 | When the password is reset successfully, then the user can log in with the new password. | Completed
F4 | 4.1 | Profile Edit | User Management | AC1 | When valid profile information is submitted, then the profile is updated successfully. | Completed
F4 | 4.1 | Profile Edit | User Management | AC2 | When invalid information is entered, then validation errors are displayed. | Completed
F4 | 4.1 | Profile Edit | User Management | AC3 | When changes are saved, then the updated information is displayed in the profile. | Completed
F4 | 4.1 | Profile Edit | User Management | AC4 | When the update fails, then an error message is shown. | Completed
F5 | 5.1 | Role-Based Dashboard Redirect | Dashboard | AC1 | When a Sender logs in successfully, then the Sender dashboard is displayed. | Completed
F5 | 5.1 | Role-Based Dashboard Redirect | Dashboard | AC2 | When an Employee logs in successfully, then the Employee dashboard is displayed. | Completed
F5 | 5.1 | Role-Based Dashboard Redirect | Dashboard | AC3 | When a Manager logs in successfully, then the Manager dashboard is displayed. | Completed
F5 | 5.1 | Role-Based Dashboard Redirect | Dashboard | AC4 | When an Admin logs in successfully, then the Admin dashboard is displayed. | Completed
F6 | 6.1 | Order Form Submission | Order Management | AC1 | When all required order details are provided, then a new order is created successfully. | Completed
F6 | 6.1 | Order Form Submission | Order Management | AC2 | When required fields are missing, then validation errors are displayed. | Completed
F6 | 6.1 | Order Form Submission | Order Management | AC3 | When an order is created, then a unique tracking ID is generated. | Completed
F6 | 6.1 | Order Form Submission | Order Management | AC4 | When the order is submitted successfully, then the order status is set to Pending. | Completed
F7 | 7.1 | Forgot password | Authentication | AC1 | When a registered email is entered, then a password recovery process is initiated. | Completed
F7 | 7.1 | Forgot password | Authentication | AC2 | When the email is not registered, then an error message is displayed. | Completed
F7 | 7.1 | Forgot password | Authentication | AC3 | When a new valid password is submitted, then the password is updated successfully. | Completed
F7 | 7.1 | Forgot password | Authentication | AC4 | When the password is changed successfully, then the user can log in using the new password. | Completed
F8 | 8.1 | Sender Order History | Order Management | AC1 | When a Sender accesses order history, then all current and past orders are displayed. | Completed
F8 | 8.1 | Sender Order History | Order Management | AC2 | When no orders exist, then an appropriate message is shown. | Completed
F8 | 8.1 | Sender Order History | Order Management | AC3 | When orders are displayed, then their statuses are visible. | Completed
F8 | 8.1 | Sender Order History | Order Management | AC4 | When an order is selected, then detailed information is displayed. | Completed
F9 | 9.1 | Public Parcel Tracking | Tracking & Logistics | AC1 | When a valid tracking ID is entered, then the parcel status is displayed. | Completed
F9 | 9.1 | Public Parcel Tracking | Tracking & Logistics | AC2 | When an invalid tracking ID is entered, then an error message is displayed. | Completed
F9 | 9.1 | Public Parcel Tracking | Tracking & Logistics | AC3 | When tracking information is available, then the latest location is shown. | Completed
F9 | 9.1 | Public Parcel Tracking | Tracking & Logistics | AC4 | When tracking is accessed, then login is not required. | Completed
F10 | 10.1 | Order Cancellation | Order Management | AC1 | When an order has not been picked up, then the Sender can cancel it. | Completed
F10 | 10.1 | Order Cancellation | Order Management | AC2 | When an order is already picked up, then cancellation is denied. | Completed
F10 | 10.1 | Order Cancellation | Order Management | AC3 | When cancellation is successful, then the order status changes to Cancelled. | Completed
F10 | 10.1 | Order Cancellation | Order Management | AC4 | When an order is cancelled, then a confirmation message is displayed. | Completed
F11 | 11.1 | Assigned Orders View | Operations | AC1 | When an Employee accesses assigned orders, then all assigned orders are displayed. | Completed
F11 | 11.1 | Assigned Orders View | Operations | AC2 | When no orders are assigned, then an appropriate message is shown. | Completed
F11 | 11.1 | Assigned Orders View | Operations | AC3 | When an order is selected, then detailed order information is displayed. | Completed
F11 | 11.1 | Assigned Orders View | Operations | AC4 | When assignments change, then the list updates accordingly. | Completed
F12 | 12.1 | Transit Checkpoint Status Update | Tracking & Logistics | AC1 | When Station Staff updates a parcel status, then the tracking log is updated. | Completed
F12 | 12.1 | Transit Checkpoint Status Update | Tracking & Logistics | AC2 | When a status update is saved, then the branch location is recorded. | Completed
F12 | 12.1 | Transit Checkpoint Status Update | Tracking & Logistics | AC3 | When a status update is saved, then the timestamp is recorded. | Completed
F12 | 12.1 | Transit Checkpoint Status Update | Tracking & Logistics | AC4 | When invalid status information is entered, then an error message is displayed. | Completed
F13 | 13.1 | Delivery Confirmation & Timestamp | Tracking & Logistics | AC1 | When a parcel is delivered, then the Employee can mark it as Delivered. | Completed
F13 | 13.1 | Delivery Confirmation & Timestamp | Tracking & Logistics | AC2 | When delivery is confirmed, then a timestamp is recorded. | Completed
F13 | 13.1 | Delivery Confirmation & Timestamp | Tracking & Logistics | AC3 | When delivery is confirmed, then the order is marked as completed. | Completed
F13 | 13.1 | Delivery Confirmation & Timestamp | Tracking & Logistics | AC4 | When delivery status is updated, then tracking information is updated. | Completed
F14 | 14.1 | Employee Order History | Operations | AC1 | When an Employee views order history, then all handled orders are displayed. | Completed
F14 | 14.1 | Employee Order History | Operations | AC2 | When no history exists, then an appropriate message is shown. | Completed
F14 | 14.1 | Employee Order History | Operations | AC3 | When an order is selected, then detailed information is displayed. | Completed
F14 | 14.1 | Employee Order History | Operations | AC4 | When history is loaded, then completed and active orders are distinguishable. | Completed
F15 | 15.1 | Active Orders Dashboard | Dashboard | AC1 | When a Manager accesses the dashboard, then all active orders are displayed. | Completed
F15 | 15.1 | Active Orders Dashboard | Dashboard | AC2 | When order statuses change, then the dashboard reflects the updates. | Completed
F15 | 15.1 | Active Orders Dashboard | Dashboard | AC3 | When no active orders exist, then an appropriate message is displayed. | Completed
F15 | 15.1 | Active Orders Dashboard | Dashboard | AC4 | When dashboard data loads, then orders are shown in real time. | Completed
F16 | 16.1 | Employee Workload Monitor | Monitoring & Admin | AC1 | When a Manager accesses workload monitoring, then active order counts are displayed for each Employee. | Completed
F16 | 16.1 | Employee Workload Monitor | Monitoring & Admin | AC2 | When assignments change, then workload counts are updated. | Completed
F16 | 16.1 | Employee Workload Monitor | Monitoring & Admin | AC3 | When an Employee has no active orders, then a count of zero is displayed. | Completed
F16 | 16.1 | Employee Workload Monitor | Monitoring & Admin | AC4 | When workload data is unavailable, then an error message is shown. | Completed
F17 | 17.1 | Order Filter by Status / Branch | Monitoring & Admin | AC1 | When a status filter is applied, then only matching orders are displayed. | Completed
F17 | 17.1 | Order Filter by Status / Branch | Monitoring & Admin | AC2 | When a branch filter is applied, then only matching branch orders are displayed. | Completed
F17 | 17.1 | Order Filter by Status / Branch | Monitoring & Admin | AC3 | When multiple filters are applied, then matching results are shown. | Completed
F17 | 17.1 | Order Filter by Status / Branch | Monitoring & Admin | AC4 | When filters are cleared, then all orders are displayed. | Completed
F18 | 18.1 | User Account Management | User Management | AC1 | When an Admin creates a user account, then the account is added successfully. | Completed
F18 | 18.1 | User Account Management | User Management | AC2 | When an Admin edits user details, then the changes are saved successfully. | Completed
F18 | 18.1 | User Account Management | User Management | AC3 | When an Admin deactivates an account, then the user can no longer log in. | Completed
F18 | 18.1 | User Account Management | User Management | AC4 | When an Admin changes a user role, then the new permissions are applied. | Completed
F19 | 19.1 | Manual Order Edit | Order Management | AC1 | When an Admin edits an order field, then the changes are saved successfully. | Completed
F19 | 19.1 | Manual Order Edit | Order Management | AC2 | When invalid data is entered, then validation errors are displayed. | Completed
F19 | 19.1 | Manual Order Edit | Order Management | AC3 | When an order is updated, then the latest information is displayed. | Completed
F19 | 19.1 | Manual Order Edit | Order Management | AC4 | When edits are made, then the modification is logged. | Completed
F20 | 20.1 | Branch Location Management | Branch & Pricing | AC1 | When an Admin adds a branch, then the branch is created successfully. | Completed
F20 | 20.1 | Branch Location Management | Branch & Pricing | AC2 | When an Admin edits a branch, then the changes are saved successfully. | Completed
F20 | 20.1 | Branch Location Management | Branch & Pricing | AC3 | When an Admin removes a branch, then it is deleted from the system. | Completed
F20 | 20.1 | Branch Location Management | Branch & Pricing | AC4 | When duplicate branch information is entered, then an error message is displayed. | Completed
F21 | 21.1 | Pricing Rule Configuration | Branch & Pricing | AC1 | When an Admin updates pricing rules, then the new rules are saved successfully. | Completed
F21 | 21.1 | Pricing Rule Configuration | Branch & Pricing | AC2 | When delivery charges are calculated, then the latest pricing rules are applied. | Completed
F21 | 21.1 | Pricing Rule Configuration | Branch & Pricing | AC3 | When invalid pricing values are entered, then validation errors are displayed. | Completed
F21 | 21.1 | Pricing Rule Configuration | Branch & Pricing | AC4 | When pricing rules change, then future orders use the updated rates. | Completed
F22 | 22.1 | Automated Email Notification | Notifications | AC1 | When a parcel status changes, then an email notification is sent automatically. | Completed
F22 | 22.1 | Automated Email Notification | Notifications | AC2 | When the Sender has a valid email address, then they receive the notification. | Completed
F22 | 22.1 | Automated Email Notification | Notifications | AC3 | When the Receiver has a valid email address, then they receive the notification. | Completed
F22 | 22.1 | Automated Email Notification | Notifications | AC4 | When email delivery fails, then the failure is logged. | Completed
F23 | 23.1 | Return-to-Sender Flow | Operations | AC1 | When a parcel cannot be delivered, then Return-to-Sender can be initiated. | Completed
F23 | 23.1 | Return-to-Sender Flow | Operations | AC2 | When Return-to-Sender is activated, then sender and receiver details are swapped. | Completed
F23 | 23.1 | Return-to-Sender Flow | Operations | AC3 | When the return process starts, then the tracking status is updated. | Completed
F23 | 23.1 | Return-to-Sender Flow | Operations | AC4 | When the return is confirmed, then the parcel follows the return delivery workflow. | Completed
F24 | 24.1 | Parcel Status History Timeline | Tracking & Logistics | AC1 | When a user views parcel details, then the complete status timeline is displayed. | Completed
F24 | 24.1 | Parcel Status History Timeline | Tracking & Logistics | AC2 | When status updates exist, then all checkpoints are shown in chronological order. | Completed
F24 | 24.1 | Parcel Status History Timeline | Tracking & Logistics | AC3 | When a timeline entry is displayed, then its location and timestamp are shown. | Completed
F24 | 24.1 | Parcel Status History Timeline | Tracking & Logistics | AC4 | When no tracking history exists, then an appropriate message is displayed. | Completed

## Sprint Plan
DOKO — SPRINT PLAN & BACKLOG
Sprint | ID | Feature Name | Module | Priority | Story Points | Status | Definition of Done | Assigned To | Frontend Integration | TDD | BDD
Sprint 1 (15 SP) — Authentication & Dashboard Foundation | [8 empty] | - | - | -
Sprint 1 | 1 | User Registration | Authentication | High | 3 | Completed | All ACs pass | Kaushal | - | - | -
Sprint 1 | 2 | User Login | Authentication | High | 3 | Completed | All ACs pass | Nischal | - | - | -
Sprint 2 | 3 | Forgot Password | Authentication | High | 2 | Completed | All ACs pass | Rujna | - | - | -
Sprint 1 | 4 | OTP-Based Password Reset | Authentication | High | 5 | Completed | All ACs pass | Unish | - | - | -
Sprint 1 | 7 | Role-Based Dashboard Redirect | Dashboard | High | 2 | Completed | All ACs pass | Laxmi | - | - | -
Sprint 2 (30 SP) — Order Management, Pricing & Profiles | [8 empty] | - | - | -
Sprint 2 | 5 | Profile Edit | User Management | High | 3 | Completed | All ACs pass | Unish | - | - | -
Sprint 2 | 9 | Order Form Submission | Order Management | High | 8 | Completed | All ACs pass | Parbat | - | - | -
Sprint 2 | 10 | Manual Order Edit | Order Management | Low | 5 | Completed | All ACs pass | Rujna | - | - | -
Sprint 2 | 11 | Order Cancellation | Order Management | High | 3 | Completed | All ACs pass | Kaushal | - | - | -
Sprint 2 | 12 | Sender Order History | Order Management | High | 5 | Completed | All ACs pass | Nischal | - | - | -
Sprint 2 | 13 | Employee Order History | Order History | Low | 5 | Completed | All ACs pass | Nischal | - | - | -
Sprint 2 | 21 | Employee Workload Monitor | Branch & Pricing | Medium | 8 | Completed | All ACs pass | Laxmi | - | - | -
Sprint 3 (26 SP) — Logistics, Operations & Admin Setup | [8 empty] | - | - | -
Sprint 3 | 6 | User Account Management | User Management | Medium | 3 | Completed | All ACs pass | Parbat | - | - | -
Sprint 2 | 15 | Parcel Status History Timeline | Tracking & Logistics | Medium | 2 | Completed | All ACs pass | Unish | - | - | -
Sprint 3 | 18 | Return-to-Sender Flow | Operations | Low | 5 | Completed | All ACs pass | Nischal | - | - | -
Sprint 2 | 20 | Branch Location Management | Branch & Pricing | Medium | 5 | Completed | All ACs pass | Kaushal | - | - | -
Sprint 3 | 23 | Order Filter by Status / Branch | Monitoring & Admin | Low | 5 | Completed | All ACs pass | Laxmi | - | - | -
Sprint 3 | 24 | Automated Email Notification | Notifications | Low | 3 | Completed | All ACs pass | Rujna | - | - | -
Sprint 4 (20 SP) — Tracking, Active Monitoring & Execution
Sprint 4 | 8 | Active Orders Dashboard | Dashboard | Medium | 5 | Completed | All ACs pass | Parbat
Sprint 4 | 16 | Transit Checkpoint Status Update | Tracking & Logistics | Low | 5 | Completed | All ACs pass | Kaushal
Sprint 4 | 17 | Delivery Confirmation&Timestamp | Tracking & Logistics | Medium | 5 | Completed | All ACs pass | Unish
Sprint 4 | 19 | Assigned Orders View | Operations | Medium | 5 | Completed | All ACs pass | Nischal
Sprint 5 (5 SP) — Refinement & Capacity Monitoring
Sprint 5 | 22 | Employee Workload Monitor | Monitoring & Admin | Low | 5 | Completed | All ACs pass | Laxmi
Sprint 5 | 9 | Public Parcel Tracking | Tracking & Logistics | Medium | 3 | Completed | All ACs pass | Nischal

## User Story Priority Hierarchy
DOKO — AGILE USER STORY HIERARCHY
Feature ID | User Story ID | Feature Name | Module | I need to <perform some task> | So that I can <achieve something> | Acceptance Criteria (Summary) | Priority
▸ PRIORITY: HIGH
F1 | 1.1 | User Registration | Authentication | register with my name, email, phone, and password | I can create a DOKO account and access the platform. | When valid registration details are submitted, then the account is created successfully. | High
F2 | 2.1 | User Login | Authentication | log in with my email and password | I can access my role-specific dashboard. | When valid email and password are entered, then the user is logged in successfully. | High
F3 | 3.1 | OTP-Based Password Reset | Authentication | request a password reset OTP to my email and use it to set a new password | I can securely regain access to my account if I forget my password. | When a registered email is submitted, then an OTP is sent to the email address. | High
F4 | 4.1 | Profile Edit | Account Management | edit my name, phone number, and address | I can keep my profile information up to date. | When valid profile information is submitted, then the profile is updated successfully. | High
F5 | 5.1 | Role-Based Dashboard Redirect | Dashboard | be automatically redirected to my role-specific dashboard after login | I can immediately see only the features relevant to my role. | When a Sender logs in successfully, then the Sender dashboard is displayed. | High
F6 | 6.1 | Order Form Submission | Order Management | fill out an order form with receiver details, parcel weight, and description | I can create a new delivery order in the system. | When all required order details are provided, then a new order is created successfully. | High
F7 | 7.1 | Forgot password | Authentication | change the password if i forgot | I can login again | When a registered email is entered, then a password recovery process is initiated. | High
F8 | 8.1 | Sender Order History | Order Management | view a list of all my past and current orders with their statuses | I can stay informed about all my deliveries in one place. | When a Sender accesses order history, then all current and past orders are displayed. | High
F10 | 10.1 | Order Cancellation | Order Management | cancel an order that has not yet been picked up | I can avoid being charged for a delivery I no longer need. | When an order has not been picked up, then the Sender can cancel it. | High
▸ PRIORITY: MEDIUM
F6 | 18.1 | User Account Management | User management | create, edit, or deactivate any user account and change their role | I can ensure the right people have the right level of access at all times. | When an Admin creates a user account, then the account is added successfully. | medium
F8 | 3.2 | Active Orders Dashboard | Dashboard | view a centralized widget of active orders | monitor current pending and in-transit parcels in real-time | Renders real-time data table/cards for active shipments, auto-refreshes, and handles empty states cleanly. | medium
F14 | 9.1 | Public Parcel Tracking | Tracking & Logistics | enter a Tracking ID on the website without logging in | I can quickly check the current status and last updated location of a parcel. | When a valid tracking ID is entered, then the parcel status is displayed. | medium
F15 | 24.1 | Parcel Status History Timeline | Tracking & Logistics | view the full status history timeline of a parcel | I can see every checkpoint it passed through from Pending all the way to Delivered. | When a user views parcel details, then the complete status timeline is displayed. | medium
F17 | 13.1 | Delivery Confirmation & Timestamp | Tracking & Logistics | mark an order as Delivered once the Receiver has the parcel | I can record the delivery timestamp and close the order. | When a parcel is delivered, then the Employee can mark it as Delivered. | medium
F19 | 11.1 | Assigned Orders View | Operations | view a list of all orders assigned to me | I can know exactly what parcels I need to pick up or deliver. | When an Employee accesses assigned orders, then all assigned orders are displayed. | medium
F20 | 20.1 | Branch Location Management | Branch & Pricing | add, edit, or remove transit branch locations | I can keep the system's network map aligned with real-world operations. | When an Admin adds a branch, then the branch is created successfully. | medium
F21 | 21.1 | Pricing Rule Configuration | Branch & Pricing | set and update pricing rules such as price per kg or per km | I can ensure delivery charges are calculated correctly and automatically. | When an Admin updates pricing rules, then the new rules are saved successfully. | medium
▸ PRIORITY: LOW
F10 | 19.1 | Manual Order Edit | Order Management | edit shipment details manually | correct mistakes or update information on pending parcels prior to dispatch. | Authorized users can modify non-critical fields; validates inputs; logs audit trail in the DB. | Low
F13 | 14.1 | Employee Order History | Order History | view a log of my past completed deliveries | reference my past workload and verify historical actions. | Fetches closed/delivered parcels tied strictly to the employee's ID; displays chronological logs with pagination. | Low
F16 | 12.1 | Transit Checkpoint Status Update | Tracking & Logistics | log intermediate transit checkpoints | mark transit progression (e.g., "Arrived at Hub") for parcels. | Courier selects status from a dropdown; successfully registers a location stamp and updates the public timeline. | Low
F18 | 23.1 | Return-to-Sender Flow | Operations | trigger a reverse logistics workflow | I can handle undeliverable parcels cleanly without creating a new order. | When a parcel cannot be delivered, then Return-to-Sender can be initiated. | Low
F22 | 16.1 | Employee Workload Monitor | Monitoring & Admin | see how many active orders each Employee currently has | I can quickly spot overloading and act before delays happen. | When a Manager accesses workload monitoring, then active order counts are displayed for each Employee. | Low
F23 | 17.1 | Order Filter by Status / Branch | Monitoring & Admin | filter orders by status or branch location | I can focus on problem areas and resolve issues faster. | When a status filter is applied, then only matching orders are displayed. | Low
F24 | 22.1 | Automated Email Notification | Notifications | receive an automatic email notification whenever my parcel's status changes | I can stay updated without having to manually check the tracking page. | When a parcel status changes, then an email notification is sent automatically. | Low